## Sheet1
Sr. No | Date | Sonika Varma | Rohan Dhanani
1 | 2023-08-04 | Discussion About Project | Discussion About Project | Project Name :- LiveCode-Compiler
2 | 2023-08-05 | Discussion About Project | Discussion About Project
3 | 2023-08-06 | Sunday Break | Sunday Break
4 | 2023-08-07 | Project Picked | Project Picked | Project Destribution
5 | 2023-08-08 | Discussion About Selected Project | Discussion About Selected Project | Names | Distribution
6 | 2023-08-09 | Discussion About Selected Project | Discussion About Selected Project | Sonika Varma (Leader) | Back-End ( Node.js, Socket.io, Mongodb)
7 | 2023-08-10 | Search About Project In Google | Search About Project In Youtube | Rohan Dhanani | Front-End ( React.js )
8 | 2023-08-11 | Search About Project In Github | Search About Project In Youtube
9 | 2023-08-12 | Search About Project In Youtube | Search About Project In Youtube
10 | 2023-08-13 | Sunday Break | Sunday Break
11 | 2023-08-14 | Synopsis Discussion | Synopsis Discussion
12 | 2023-08-15 | No Work ( Independence Day ) | No Work ( Independence Day )
13 | 2023-08-16 | Discussion About Use Case Diagram | Discussion About Use Case Diagram
14 | 2023-08-17 | Create 1 Level DFD | Create 1 Level DFD
15 | 2023-08-18 | Checked 0 Level DFD | Checked 1 Level DFD
16 | 2023-08-19 | Working On Database Schema | Working On UI Module
17 | 2023-08-20 | Sunday Break | Sunday Break
18 | 2023-08-21 | Validate Database Schema | Working On UI Module
19 | 2023-08-22 | Create MVC Structure | Trying To Implement Compiler
20 | 2023-08-23 | Configure Server | Trying To Implement Compiler
21 | 2023-08-24 | Help To Solving Error Of DuplicateCompiler | Solving Error Of DuplicateCompiler
22 | 2023-08-25 | Help To Solving Error Of DuplicateCompiler | Solving Error Of DuplicateCompiler
23 | 2023-08-26 | Configure Route For API | User Interface Error Of Compiler
24 | 2023-08-27 | Sunday Break | Sunday Break
25 | 2023-08-28 | Create API Using Socket.io for Live Room | Create UI For Compiler Room
26 | 2023-08-29 | Create API Using Socket.io for Live Room | Create UI For Compiler Room
27 | 2023-08-30 | No Work ( Raksha Bandhan Holiday ) | No Work ( Raksha Bandhan Holiday )
28 | 2023-08-31 | Implement Socket.io API | Implementing Socket io API
29 | 2023-09-01 | Implement Socket.io API | Implementing Socket io API
30 | 2023-09-02 | Solve Error In Socket.io API | Solve Error In Socket.io API
31 | 2023-09-03 | Sunday Break | Sunday Break
32 | 2023-09-04 | Creatre Register API Schema | Create Register Page UI
33 | 2023-09-05 | Creatre Register API | Create Register Page UI
34 | 2023-09-06 | No Work ( Janmashtami ) | No Work ( Janmashtami )
35 | 2023-09-07 | No Work ( Janmashtami ) | No Work ( Janmashtami )
36 | 2023-09-08 | Creatre Login API Schema | Create Login Page UI
37 | 2023-09-09 | Create Login API | Create Login Page UI
38 | 2023-09-10 | Sunday Break | Sunday Break
39 | 2023-09-11 | Register Page API Intigration | Register Page API Intigration
40 | 2023-09-12 | Login Page API Intigration | Login Page API Intigration
41 | 2023-09-13 | Add Runtime Compiler | Add Runtime Compiler
42 | 2023-09-14 | Add Runtime Compiler | Add Runtime Compiler
43 | 2023-09-15 | Solve Error In Compiler | No Work ( illness )
44 | 2023-09-16 | Solve Error In Compiler | Solve Error In Compiler
45 | 2023-09-17 | Sunday Break | Sunday Break
46 | 2023-09-18 | Add Language Selection Portion | Add Language Selection Portion
47 | 2023-09-19 | No Work ( Ganesh Chaturthi ) | No Work ( Ganesh Chaturthi )
48 | 2023-09-20 | Add Theme Selection Portion | Add Theme Selection Portion
49 | 2023-09-21 | Add Theme Selection Portion | Add Theme Selection Portion
50 | 2023-09-22 | Create Send OTP API | Create Send Mail Page UI
51 | 2023-09-23 | Solve Gmail Login Error For Send Mail | Create Send Mail Page UI
52 | 2023-09-24 | Sunday Break | Sunday Break
53 | 2023-09-25 | Create Forget Password API | Create Forget Password Page UI
54 | 2023-09-26 | Solve Login Token Issue | Create Forget Password Page UI
55 | 2023-09-27 | No Work ( Ganesh visrjan ) | No Work ( Ganesh visrjan )
56 | 2023-09-28 | No Work ( Ganesh visrjan ) | No Work ( Ganesh visrjan )
57 | 2023-09-29 | Intigrate Send Mail API | Intigrate Send Mail API
58 | 2023-09-30 | Intigrate Forget Password API | Intigrate Forget Password API
59 | 2023-10-01 | Sunday Break | Sunday Break
60 | 2023-10-02 | No Work ( Holiday ) | No Work ( Holiday )
61 | 2023-10-03 | Solve Issue In Encription Of Password | Create Home Page UI
62 | 2023-10-04 | Create Contact API | Create Home Page UI
63 | 2023-10-05 | Create Contact API | Create Home Page UI
64 | 2023-10-06 | Write About Contant For UI | Create About US Page UI
65 | 2023-10-07 | Write About Contant For UI | Create About US Page UI
66 | 2023-10-08 | Sunday Break | Sunday Break
67 | 2023-10-09
68 | 2023-10-10
69 | 2023-10-11
70 | 2023-10-12
71 | 2023-10-13
72 | 2023-10-14